## Slide 2
DX
WFS sensor
Refurbished Pockels cells in
Mount sensors
Calibration unit alignment
IM aquisition / Tuning
Closed loop test on Calib unit
Closed loop on sky
New Pockels cells in
Entrance window adjustment
Dichroic garage
TT unit:
Fibre rooting
Functional tests
IM with cal unit
Performance test with Cal unit
On sky test
TT from Pyramid
Truth sensing
Algorithm development
Implementation SW
Test & Gui etc
Launch
LM Motors refurbish
Thermocouples
Corrector & motor controller upgrade
Vibration compensation
Position control loop
Focussing loop
SX
WFS sensor
Pockels cells in
Lab tests
Mount sensors
Calibration unit alignment
IM aquisition
Closed loop test on Calib unit
Closed loop on sky
TT unit:
Lenslet glueing etc..
APD installation
Fibre rooting
Functional tests
IM with cal unit
Performance test with Cal unit
On sky test
Truth sensing
Launch
Motors refurbish
Thermocouples
Corrector
Vibration compensation
System
General Functionality
Operations optimization
High level Arbitrator
Overview & Status GUI
AO performance
Binocular ARGOS operation
Science demonstration
Tbad implementation
System performance tools
Atmosphere characterization

## Slide 3: when
Oct | Nov | Feb | May | June/July | Summer | Oct | Nov
DX WFS Inst. | DX LGS closed loop | TT, truth, LGS closed loop vibration | System tests | DX Observation tests | TT installation | SX | SX+DX
 | Vibration | LM1 ref. | SX Cal unit align | SX installation |  |  | 
 |  | SX axis alignment |  |  |  |  | 
2014
2015