## Slide 1: 8am: start testing the corner cube mounts on DX cells

## Slide 2: 9am: dichroic rails cleaning and deployment test

## Slide 3: 9:30am: DX mount pulled out from clean room

## Slide 4: 9:45am: DX mount attached to handling tool in high bay and lifted with dome crane

## Slide 5: Total weight of the structure 432kg, preload to 388kg before loose M16 screws

## Slide 6: 9:56am: the DX mount is in the dome

## Slide 7: Fly over SX eye

## Slide 8: Behind telescope, over gallery, over DX eye (10:05am)

## Slide 9: 2 people dress up: 1 hanged to LBTI, 1 on LGSW table

## Slide 10: 10:15: the DX mount is pulled toward interfaces

## Slide 11: It fits easily

## Slide 12: 10:22am: counterweight retracted

## Slide 13: 10:27am: halding tool removed

## Slide 15: 10:45am: 2 people are ready in the basket

## Slide 16: Basket approaches the DX mount to swing in the fold mirror: 2 people stabilize it with ropes

## Slide 17: Fold mirror motor removed and arm retracted (10:56am)

## Slide 18: 11:15am: LUCI 2 cal unit deployed -> OK

## Slide 19: 11:30am: LUCI 2 rotator moved by 360deg -> OK
25mm clearence to AGW cover(22.5 from model)

## Slide 20: 12am: LUCI 1 cal unit deplyed and distances to dichroic interfaces measured
786mm
1220mm
54mm ??
2016mm

## Slide 21: 1:15pm: horizon test for DX, LUCI 2 rotator moved by 360deg -> OK

## Slide 22: 1:30pm: unobstructed volume check (still to be measured from images, yellow tape is 50cm)

## Slide 23: Afternoon:
SX mount in clean room
Dummies on SX cells with covers
Dichroic rails cleaned and cart slided
Connectors label plate installed
Fold mirror manually deployed
Rust inibitor on rusty parts (not done on DX mount!)
SX ready to be installed at telescope on Wednesday 5th