Installation plan for February 2014

Doc. No.	 ARGOS Note 120

Issue		 1.0

Date		 17/01/2014

Prepared	M. Bonaglia 		2014/01/17

Name				Date

Reviewed	S. Esposito, L.Busoni	2014/01/17

Name				Date

TABLE OF CONTENTS

1	Scope	2

2	Applicable documents	2

3	Personal Involved	3

4	Daily activity resume	3

Monday February, 3rd	4

Tuesday February, 4th	6

Wednesday February, 5th	7

Thursday February, 6th	9

Friday February, 7th	10

Saturday February, 8th	11

Sunday February, 9th	12

Change Record

| Issue | Date | Section/ Paragraph Affected | Reasons / Remarks | Name |
| --- | --- | --- | --- | --- |
| 1.0 | 17.01.2014 | all | created | M. Bonaglia |

# Scope

This document details the telescope activities involving the ARGOS systems scheduled for February 2014.

# Applicable documents

| No. | Title | Number & Issue |
| --- | --- | --- |
| AD 1 | ARGOS_dichroic_installation.pdf |  |
| AD 2 |  |  |

# Personal Involved

GN: Giovanni Negrini, Tomelleri s.r.l.

INAF: Marco Bonaglia (MB), Enrico Pinna (EP), Lorenzo Busoni (LB)

AE: ARGOS engineer (Gustavo Rahmer, Michael Lefebvre)

CO: Crane Operator (?, LBTO)

TO: Telescope Operator (?, LBTO)

LO: Laser tracker operator (Lee Dettmann)

# Daily activity resume

1st week:

|  | Sun 2nd | Mon 3rd | Tue 4th | Wed 5th | Thu 6th | Fri 7th | Sat 8th |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MORNING |  | Dichroic unpacking in high bay area | Platform installation on DX side (7:30-9:30 am) | Platform installation on DX side (7:30-9:30 am) | Platform installation on SX side (7:30-9:30 am) | Platform installation on DX side (7:30-9:30 am) | Laser tracker alignment of DX dichroic |
|  |  |  | On telescope activity, DX side | On telescope activity, DX side | On telescope activity, SX side | On telescope activity, SX side |  |
| AFTERNOON | GN, MB, EP arrival at LBT | DX mount test in clean room | Platform removal (12:30am-2:30pm) | Platform removal (11:0am-1:00pm) | Platform removal (12:30am-2:30pm) | Platform removal (11:00am-1:00pm) |  |
|  |  |  | On telescope activity, DX side | On telescope activity, DX side | On telescope activity, SX side | On telescope activity, SX side |  |
| EVENING |  |  |  | SX mount test in clean room |  |  |  |

2nd week:

|  | Sun 9th | Mon 10th | Tue 11th | Wed 12th | Thu 13th | Fri 14th | Sat 15th |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MORNING | Laser tracker alignment of SX dichroic |  |  |  |  |  |  |
| AFTERNOON |  |  |  |  |  |  |  |
| EVENING |  |  |  |  |  |  |  |

# Monday February, 3rd

This day the dichroic box is unpacked in the high bay, the functionality of DX mount is tested in clean room and it is prepared for next day installation on telescope.

Start of activities: 8:00 a.m.

| # | Description | By | Area | Req | End time |
| --- | --- | --- | --- | --- | --- |
|  | Unpacking of dichroic box: - handling tool - 2x stands - 2x dichroic mounts - control electronics - 2x optic dummies | GN, INAF, AE, CO | High bay | Crane(or fork lift) | 10:00 a.m. (2.0h) |
| 1.1. | Hanging of handling tool to high bay crane | CO | High bay | Crane |  |
|  | Unpacking and storage of mounts and optics box: - 2x dichroic and 2x fold mirror cells - 3x dichroic optic, 2x fold mirror optic | GN, INAF, AE | High bay & clean room |  | 10:30 a.m. (0.5h) |
|  | Switch of DX mount from storage stand to reclining stand: - Mount DX cells on DX mount - Install dummies on DX cells - Connect cables and controller to DX mount - Slide out fold mirror - Disconnect cables - Hang mount on handling tool - Switch stand | GN, INAF, AE, CO | High bay | 110V, crane with handling tool | 12:00 a.m. (1.5h) |
|  | Move and setup DX mount to clean room: - Connect controller and cables | GN, INAF, AE | High bay | 110V | 12:30 a.m. (0.5h) |
| 4.1. | Move handling tool to dome level 5 with crane | CO | High bay- dome | Crane |  |
|  | Check controller connectivity and functionality in remote | GN, INAF, AE | Clean room |  | 1:00 p.m. (0.5h) |
|  | DX mount functionality test in manual control (dummies on): - Dichroic deployment - End stop functionality - Fold mirror deployment - End stop functionality | GN, INAF, AE | Clean room |  | 1:30 p.m. (0.5h) |
|  | DX mount functionality in remote control (dummies on): - Dichroic deployment - Dichroic limit switch signal activation - Fold mirror deployment - Fold mirror limit switch signal activation | GN, INAF, AE | Clean room |  | 2:00 p.m. (0.5h) |
|  | Remove dummies from DX cells, clean DX cells | GN | Clean room |  | 2:30 p.m. (0.5h) |
| 8.1. | Check and clean optics | INAF | Clean room |  |  |
|  | Optics installation in DX cells | GN, INAF, AE | Clean room |  | 3:00 p.m. (0.5h) |
|  | Corner cube mounts installation on DX cell and optic covers adjustment | GN, INAF, AE | Clean room |  | 3:30 p.m. (0.5h) |
|  | Move DX mount to dome level 5 with elevator | GN, INAF, AE | Dome | Elevator | 3:45 p.m. (0.25h) |
| 11.1. | Move controller and cables to dome level 5 | GN, INAF, AE | Dome |  |  |
|  | Prepare DX mount for lifting: - Connect cables and controller - Slide out fold mirror | GN, INAF, AE | Dome | 110V | 4:00 p.m. (0.5h) |
| 12.1. | Prepare and move balcony to dome level 5 | CO | Dome |  |  |

# Tuesday February, 4th

The day task is to install the DX mount on the instrument gallery and check that the LUCI rotator can be operated safely with the mount installed.

Start of activities: 7:30 a.m.

NOTE: 8h of activity on the telescope structure are scheduled. To be able to leave the dome area at 4:00 p.m. it is required to start operation maximum at 8:00 a.m. (7:30 a.m. is preferred to have contingency time).

| # | Description | By | Area | Req | End Time |
| --- | --- | --- | --- | --- | --- |
|  | Balcony installation on DX eye | CO, TO | Dome | Crane | 9:30 a.m. (2.0h) |
| 13.1. | Controller and cables setup on instrument gallery | GN, INAF | Inst. Gall |  |  |
|  | Install DX mount on instrument gallery: - Hang handling tool to crane - Lift DX mount to instrument gallery - Bolt DX mount to interface pads - Remove handling tool | GN, INAF, AE | Inst. Gall. | Crane, handling tool | 11:00 a.m. (1.5h) |
|  | DX mount test #1 at Zenith: - Connect cables and controller - Functionality test of dichroic and fold mirror | GN, INAF, AE | Inst. Gall. |  | 11:30 a.m. (0.5h) |
|  | Test possible collisions with AGW structure at Zenith with parked dichroic: - Rotate LUCI rotator by 360° - Deploy LUCI cal. Unit | GN, INAF, AE, TO | Inst. Gall. & control room | Remote | 12:30 a.m. (1h) |
|  | Remove balcony from DX eye | CO, TO | Dome | Crane | 2:30 p.m. (2h) |
| 17.1. | Remove cables and controller from instrument gallery | GN, INAF | Inst. Gall. |  |  |
|  | Move telescope at horizon and check for collisions with AGW structure |  |  |  | 3:00 p.m. (0.5h) |
|  | Move telescope to Zenith and check of the status of DX mount before observing night |  |  |  | 3:30 p.m. (0.5h) |

# Wednesday February, 5th

Functionality of DX mount is tested both at Zenith and horizon. To secure the operations at Zenith the balcony should be installed. To check the mount behavior at horizon we expect to be able to reach the front bent Gregorian station with the scissor lift.

Start of activities: 7:30 a.m.

NOTE: 8h of activity on the telescope structure are scheduled. To be able to leave the dome area at 4:00 p.m. it is required to start operation maximum at 8:00 a.m. (7:30 a.m. is preferred to have contingency time).

| # |  | Description | By |  | Area | Req |  | End Time |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Balcony installation on DX eye |  | CO, TO | Dome |  | Crane |  | 9:30 a.m. (2.0h) |
| 20.1. |  | DX mount setup for operations: - Secure and connect controller and cables - Route Ethernet cable to dome level 5 |  | GN, INAF | Inst. Gall |  | Very long eth cable, 110V |  |  |
|  |  | DX mount test #2 at Zenith: - Measure unobstructed volume - Measure deployment time - Stress test (move back and forth) - Measure deployment accuracy and repeatability | GN, INAF, AE |  | Inst. Gall. |  |  | 10:30 a.m. (1h) |  |
|  |  | Test possible collisions with AGW structure at Zenith with deployed dichroic: - Rotate LUCI rotator by 360°d | GN, INAF, AE, TO |  | Inst. Gall & control room | Remote |  | 11:00 a.m. (0.5h) |  |
|  |  | Remove balcony from DX eye | CO, TO |  | Dome | Crane |  | 1:00 p.m. (2h) |  |
|  |  | DX mount test #3 at horizon: - Measure deployment time - Stress test (move back and forth) - Measure deployment accuracy and repeatability (?) | GN, INAF, AE, CO |  | Inst. Gall. | Scissor lift |  | 2:30 p.m. (1.5h) |  |
|  |  | Test possible collisions with AGW structure at horizon with deployed dichroic: - Rotate LUCI rotator by 360°d | GN, INAF, AE, TO |  | Inst. Gall & control room | Remote, scissor lift |  | 3:00 p.m. (0.5h) |  |
|  | Move telescope to Zenith and check of the status of DX mount before observing night: - Remove cables and controller |  |  | GN, INAF, AE | Inst. Gall |  |  |  | 3:30 p.m. (0.5h) |

Second part of the day activity is performed in clean room to check the functionality of the SX mount and to prepare it for next day installation on telescope.

|  | Move and setup SX mount to clean room on storage stand: - Connect controller and cables - Mount SX cells - Install dummies on SX cells - Install covers | GN, INAF, AE | Clean room | 110V | 4:00 p.m. (0.5h) |
| --- | --- | --- | --- | --- | --- |
|  | SX mount functionality test: - Dichroic deployment - End stop functionality - Dichroic limit switch signal activation - Fold mirror deployment - End stop functionality - Fold mirror limit switch signal activation | GN, INAF, AE | Clean room |  | 5:00 p.m. (1h) |

# Thursday February, 6th

The day task is to install the SX mount on the instrument gallery and check that the LUCI rotator can be operated safely with the mount installed.

Start of activities: 7:30 a.m.

NOTE: 8h of activity on the telescope structure are scheduled. To be able to leave the dome area at 4:00 p.m. it is required to start operation maximum at 8:00 a.m. (7:30 a.m. is preferred to have contingency time).

| # | Description | By |  | Area | Req | End Time |
| --- | --- | --- | --- | --- | --- | --- |
|  | Balcony installation on SX eye | CO, TO |  | Dome | Crane | 9:30 a.m. (2.0h) |
| 29.1. | Move SX mount, controller and cables to dome level 5 | GN, INAF |  | Dome | 110V |  |
| 29.2. | Prepare SX mount for lifting: - Connect cables and controller - Slide out fold mirror |  | GN, INAF, AE | Dome |  |  |
| 29.3. | Move controller and cables to instrument gallery |  | GN, INAF, AE | Inst. Gall. |  |  |
|  | Install SX mount on instrument gallery: - Hang handling tool to crane - Lift SX mount to instrument gallery - Bolt SX mount to interface pads - Remove handling tool | GN, INAF, AE |  | Inst. Gall. | Crane, handling tool | 11:00 a.m. (1.5h) |
|  | SX mount test #1 at Zenith: - Connect cables and controller - Functionality test of dichroic and fold mirror | GN, INAF, AE |  | Inst. Gall. |  | 11:30 a.m. (0.5h) |
|  | Test possible collisions with AGW structure at Zenith with parked dichroic: - Rotate LUCI rotator by 360° - Deploy LUCI cal. Unit | GN, INAF, AE, TO |  | Inst. Gall. & control room | Remote | 12:30 a.m. (1h) |
|  | Remove balcony from DX eye | CO, TO |  | Dome | Crane | 2:30 p.m. (2h) |
| 33.1. | Remove cables and controller from instrument gallery | GN, INAF |  | Inst. Gall. |  |  |
|  | Move telescope at horizon and check for collisions with AGW structure |  |  |  |  | 3:00 p.m. (0.5h) |
|  | Move telescope to Zenith and check of the status of SX mount before observing night |  |  |  |  | 3:30 p.m. (0.5h) |

# Friday February, 7th

Functionality of SX mount is tested both at Zenith and horizon. To secure the operations at Zenith the balcony should be installed. To check the mount behavior at horizon we expect to be able to reach the front bent Gregorian station with the scissor lift.

Start of activities: 7:30 a.m.

NOTE: 8h of activity on the telescope structure are scheduled. To be able to leave the dome area at 4:00 p.m. it is required to start operation maximum at 8:00 a.m. (7:30 a.m. is preferred to have contingency time).

| # |  | Description | By |  | Area | Req |  | End Time |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Balcony installation on SX eye |  | CO, TO | Dome |  | Crane |  | 9:30 a.m. (2.0h) |
| 36.1. |  | SX mount setup for operations: - Secure and connect controller and cables - Route Ethernet cable to dome level 5 |  | GN, INAF | Inst. Gall |  | Very long eth cable, 110V |  |  |
|  |  | SX mount test #2 at Zenith: - Measure unobstructed volume - Measure deployment time - Stress test (move back and forth) - Measure deployment accuracy and repeatability | GN, INAF, AE |  | Inst. Gall. |  |  | 10:30 a.m. (1h) |  |
|  |  | Test possible collisions with AGW structure at Zenith with deployed dichroic: - Rotate LUCI rotator by 360°d | GN, INAF, AE, TO |  | Inst. Gall & control room | Remote |  | 11:00 a.m. (0.5h) |  |
|  |  | Remove balcony from SX eye | CO, TO |  | Dome | Crane |  | 1:00 p.m. (2h) |  |
|  |  | SX mount test #3 at horizon: - Measure deployment time - Stress test (move back and forth) - Measure deployment accuracy and repeatability (?) | GN, INAF, AE, CO |  | Inst. Gall. | Scissor lift |  | 2:30 p.m. (1.5h) |  |
|  |  | Test possible collisions with AGW structure at horizon with deployed dichroic: - Rotate LUCI rotator by 360°d | GN, INAF, AE, TO |  | Inst. Gall & control room | Remote, scissor lift |  | 3:00 p.m. (0.5h) |  |
|  | Move telescope to Zenith and check of the status of SX mount before observing night: - Remove cables and controller |  |  | GN, INAF, AE | Inst. Gall |  |  |  | 3:30 p.m. (0.5h) |

# Saturday February, 8th

Start of activities: 8:00 a.m.

| # | Description | By | Area | Req | End Time |
| --- | --- | --- | --- | --- | --- |
|  | Bring cables and controller to instrument gallery, connect them to DX mount | GN, INAF, AE | Inst. Gall. | 110V power cord | 8:30 a.m. (0.5h) |
|  | Install laser tracker on DX eye | LO, LB, INAF | Dome |  |  |
|  | Calibrate LT: - Origin on LUCI axis, in natural focus - Z axis along LUCI axis, toward focus - Y axis parallel to M1 plane, towards C-ring - X axis perpendicular to M1 plane, toward M2 |  | Dome |  |  |
|  | Put DX dichroic in work position |  |  |  |  |
|  | Measure of the 3 points on the DX dichroic cell, work position |  |  |  |  |
|  | Put dichroic in parked position |  |  |  |  |
|  | Measure of the 3 points on the DX dichroic cell, parked position |  |  |  |  |
|  | Remove the 3 SMR mounts from DX dichroic cell |  |  |  |  |
|  | Install the 3 SMR mounts on DX LGSW table |  |  |  |  |
|  | Measure the 3 points on the DX LGSW table |  |  |  |  |

# Sunday February, 9th

Start of activities: 8:00 a.m.

| # | Description | By | Area | Req | End Time |
| --- | --- | --- | --- | --- | --- |
|  | Bring cables and controller to instrument gallery, connect them to SX mount | GN, INAF, AE | Inst. Gall. | 110V power cord | 8:30 a.m. (0.5h) |
|  | Install laser tracker on SX eye | LO, LB, INAF | Dome |  |  |
|  | Calibrate LT: - Origin on LUCI axis, in natural focus - Z axis along LUCI axis, toward focus - Y axis parallel to M1 plane, towards C-ring - X axis perpendicular to M1 plane, toward M2 |  | Dome |  |  |
|  | Put SX dichroic in work position |  |  |  |  |
|  | Measure of the 3 points on the SX dichroic cell, work position |  |  |  |  |
|  | Put dichroic in parked position |  |  |  |  |
|  | Measure of the 3 points on the SX dichroic cell, parked position |  |  |  |  |
|  | Remove the 3 SMR mounts from SX dichroic cell |  |  |  |  |
|  | Install the 3 SMR mounts on SX LGSW table |  |  |  |  |
|  | Measure the 3 points on the SX LGSW table |  |  |  |  |

End of document