## Tabelle1
Daytime
Switch on DX and SX LGSW, check HW status, PC test
Clean/derust stuff after water catastrophy
Mount BCUs
Test BCUs
Switch on DX and SX FLAO
Try closed loop on SX
Implement new FoV center measurement on DX
Save jitter initial position
DX-LGSW AO calibration & test
Acquire LGSW IM
Combine RECs, test LGSW only, test LGSW+PYR
DX-QC calibration & test
Measure QC IM
Verify copointing
Define hotspots on CCD47 for NGS acquisition
Test LGSW+QC, PYR vs QC test
Truth Sensing test
Check behaviour of CCD39 @25Hz
Optimize gain and integration time at low flux
Implement new diagnostic in Zabbix (True modes)
Check Pause NGS behaviour
Port new Truth Sensing features on SX
measure timescales from distortion to reaction (BCU vibration comp)
implement BCU to pupil vib comp
Training
Matthias
Nighttime
Functional test / SX
Functional test / DX
Functional Binocular test…..
vibration comp measurements
Laser flexure comp SX/DX in bino mode…!
Observation tests
8o c lock / SX/DX
UDS fields/ rotation curves
CL224, SDSS J0143+1607
Maffei
IC342
Mech tasks
Water connectors Racks
Sealing LM1 housing
Moth hotel
Grease LM1 motor screws
Beam compensator position check
Water service innolas lasers
Inventory 3L and cleanup
Inventory 3U