## open
Task/ Action | Additional description | Responsible | Status | comments
General tasks
Spare list | Spare parts list check | HG / JZ / MB
Laser test bench | find a location at LBT / Setup the bench | GR
Documentation | check the status of our documentation/ manuals | HG
FLAO vignetting of the Luci field | measurement done by Iskren: make a document out of that. Advise observing with argos on guide star placement | SR/IG
Firmware | Where to archive PLC software and other firmware | GR
Documentation | All drawings into CAN archive | MD
Water | Bypass cooling water, professionalize valve | HG
Cooling | Service of Laser coolers/ water Filters | GR
AAS
Delay generation | hardware delay generation for TBAD signals | JZ
Vibration compensation
latencys | measure delays | MR
BCU | check on best interface | MR
PZT | replace PZT drivers for pupil mirror | MR/JZ
Laser system
covers | replace failed panels- needed? | MD
cooling | bypass wasser professionalisieren | HG
Spares | test spare lasers at LBT. Optimize SHG temp. | GR
launch system
LM replacement | start the process, discussion & requirement paper on why how etc | SR
Pockels
Spares | production of mechanics for the spares | MD
Spares | optics core production | SR
Drivers | find out what causes the death- replace switches? | JZ
CCD & BCU
Italy installation of CCDs |  | Gox, Jz | 1 done
water connections | secure and fix the swagelock cooling tubes | MD
vacuum leakage | find leak? Install pump? Find small pump? | HG
spare BCU | get it back from Bozen and test it | MB/MR
WFS
Spare Rack | where is it? | JZ
Spare Rack | do we have everything to fill it? | JZ
loop stability | what happens in the zero flux case on the WFS???? How to deal with it | LB
TT sys
fibres | spare fibres from Potsdam | GR
Misc
Interlock | Luci cal to Dichroic interlock switch failes often. Fix the switches? | JZ
Rain covers | production of professional rain coats for all our units. | MD
cabnle channels | close channels at WFS | MB
FLAO wobble | measurement and compensation of the FLAO-to mask wobble | AC/LB/
APD wobble | measurement and compensation of the APD-to mask wobble
FLAO stages | compensation of the Flao stage flexure when not powered (do we need that?) | LB
LuciCal-interlock | dichroic interlock switch problems | MB
computers
operations | install new operations center | JB
LBT SW tasks day December
status gui |  | JB
tcs interface | populate dd | JB
mount coords from dd | solve detxy….issues | JB
solve LAT cam problems | and issues that may follow out of that(the loss of heater, shutters etc) | JB
Luci stuff | anything more related to Luci
dead SSD | Luci SSD exchange | PB
mask alignment | CR pixel location needs to be known | SR
Flexure | active flexure compensation preparation for 3.75 cam | SR/WG
LM motors | tools preparation for LM motor exchanges | MD
LMS | take thermal contraction into acount | ReH/SR
| Luci1/2 Pixelscale taken properly into account? ISF files | ReH/SR
| Luci1/luci2 conversion of Maskfiles | ReH/SR
| tel. plane plate scale known to high accuracy? | ReH/SR
| crosscheck mask alignment with offline software | SR
| enable the new LMS at Luci to take all alignment stars | SR
smaller mask ID?
smaller alignment holes?
active flex comp slit into LMS?
offsets | measure dither needs for LS observations: alignment slit to detector
DetX DetY offsets: how do we realy move on the detector?
focus | Luci focus all gratings and filters needed
Binocular
Bino obs | scripting needs evaluation-> what is our scheme to create bino scripts? | WG
December nighttime LBT