## Tabelle1
Month | June | [10 empty] | July
date |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
day |  | Sun | Mon | Tu | Wed | Thu | Fr | Sa | Su | Mon | Tu | Wed | Thu | Fri | Sat | su | mon | Tue
|  | Daytime activities | [10 empty] | night argos |  |  |  |  | Leaving LBT
|  | SX LM1 Motor Upgrade & LM2 DX heater installation | [5 empty] | Contingency
Daytime activities |  | Crew arrives afternoon. Material and tools check, inspection of SX LM1 unit. | Opening LM1, Mirror fixing, distance measurement | Motor exchange SX dust tubes upgrade with baffles. | Motor exchange, SX dust tubes upgrade with baffles. | End switch mount and adjustment, Motor movement test, SX dust tubes upgrade with baffles. | heater LM2 installation | Contingency | TT-calibration, WFS check & calibration daytime CL test, SW work | TT-calibration, WFS check & calibration daytime CL test, SW work Dithering test possible? | TT-calibration, WFS check & calibration daytime CL test, SW work, LM2 heater connection, heater test | TT-calibration, WFS check & calibration daytime CL test, SW work, heater test | wfs sx cabling, heater check | spare parts check
Nighttime |  | July 2 Thu: Luci calibrations, Laser aquisition test, NGS aquisition test, automatic sequences testing. AO/ TT performance test on target, counter heater test; July 3 Fri: Test with 'dummy' operator. Dithering, offsetting etc. AO/ TT performance on target. Imaging & spectral performance testing; July 4 Sat: Dithering, offsetting etc. AO performance on target. Imaging & spectral performance testing. Vibration compensation performance; July 5 su: Dithering, offsetting etc. AO performance on target. Imaging & spectral performance testing. Vibration compensation.; July 6 mon: Dithering, offsetting etc. AO performance on target. Imaging & spectral performance testing
Telescope needs |  | Telescope Horizon, afternoon, 2 scissor lifts needed | Telescope at horizon, 2 scissor lifts needed | Telescope at horizon, 2 scissor lifts needed | Telescope at horizon, 2 scissor lifts needed | Telescope at horizon, 2 scissor lifts needed | Telescope at horizon, 2 scissor lifts needed |  | Dome mostly dark & quiet, calibration arm deployed, |  |  |  | Telescope Horizon daytime until ~noon, then dark & quiet | Telescope Horizon daytime until ~noon, then dark & quiet | Telescope Horizon daytime until ~noon, then dark & quiet | Telescope Horizon daytime until ~noon, then dark & quiet | Telescope Horizon daytime until ~noon, then dark & quiet
Crew |  | 21 Sun: Matthias D
Mathias H
Franz S.
Lorenzo
Marco
Wolfgang
Martin or Jose
Diethard
Michael L
Gustavo
LBTO SW staff
Gilles
Sebastian
Julian